## Backlog
ID | Title | Type | Requirement IDs | Link (Issue/PR/Commit) | Branch | Status | Owner | Created | Closed
US-01 | Get recommendations by user_id (REST) | Feature | US-01,NFR-01 | https://github.com/Artem89-spec/project-team-work/commit/b5643aa99c400817ab81b953613b97099f202ab6 | feature/mvp-rest | Backlog | Team | 2025-10-19
US-02 | Define static rule set (3 products) | Feature | US-02 | https://github.com/Artem89-spec/project-team-work/commit/b5643aa99c400817ab81b953613b97099f202ab6 | feature/static-rules | Backlog | Team | 2025-10-19
NFR-01 | Fast SQL via JdbcTemplate + caching | NFR | NFR-01 | https://github.com/Artem89-spec/project-team-work/commit/a57fd0a4d8655bfe23c9355b0910837b2adc3d32 | perf/caffeine-cache | Backlog | Team | 2025-10-19
OPS-01 | Deployment doc & env vars | Ops | OPS-01 | https://github.com/Artem89-spec/project-team-work/wiki/Deployment | docs/deploy | Backlog | Team | 2025-10-19

## In Progress
ID | Title | Type | Requirement IDs | Link (Issue/PR/Commit) | Branch | Status | Owner | Created | Closed
US-04 | Admin API for dynamic rules (CRUD) | Feature | US-04,API-01,API-02,API-03 | https://github.com/Artem89-spec/project-team-work/commit/a57fd0a4d8655bfe23c9355b0910837b2adc3d32 | feature/dynamic-rules | In Progress | Team | 2025-10-19
NFR-02 | Liquibase migrations for R/W DB | NFR | NFR-02 | https://github.com/Artem89-spec/project-team-work/commit/a57fd0a4d8655bfe23c9355b0910837b2adc3d32 | db/liquibase | In Progress | Team | 2025-10-19

## Done
ID | Title | Type | Requirement IDs | Link (Issue/PR/Commit) | Branch | Status | Owner | Created | Closed
US-03 | Telegram bot PoC: /recommend <Имя Фамилия> | Feature | US-03,BOT-01,BOT-02 | https://github.com/Artem89-spec/project-team-work/commit/225b1511eff1011533162bbdab9c838f9e6f7917 | feature/telegram-bot | Done | Team | 2025-10-19 | 2025-10-19
OPS-02 | /management/info build-info exposure | Ops | OPS-02 | https://github.com/Artem89-spec/project-team-work/commit/225b1511eff1011533162bbdab9c838f9e6f7917 | ops/build-info | Done | Team | 2025-10-19 | 2025-10-19
OPS-03 | /management/clear-caches endpoint | Ops | OPS-03 | https://github.com/Artem89-spec/project-team-work/commit/a57fd0a4d8655bfe23c9355b0910837b2adc3d32 | ops/clear-cache | Done | Team | 2025-10-19 | 2025-10-19